## Sheet1
| Building for John Smith |  |  |  |  | year | 2020-04-03
| Commercial, Residential or Farm |  |  |  |  | month | 2020-04-03
| schedule for planning (or construction) |  |  |  |  | week of | 2020-03-30 |  |  | 2020-04-06 | [6 empty] | 2020-04-13 | [6 empty] | 2020-04-20
| keep everyone up to date with schedule |  |  |  |  | week # | 1 |  |  | 2 | [6 empty] | 3 | [6 empty] | 4
| note key landmark dates |  |  |  |  | date | 2020-04-03 | 2020-04-04 | 2020-04-05 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26
| catch up on weekends |  |  |  |  | day | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| realistic availability (x persons) (- holidays) |  |  | 131 | 180 | available hours | 8 | 8 | 8 | 8 | 8 | 4 | 8 | 8 | 8 | 4 | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| insert below | hrs | reps | total | avail total
sort | Work by John Smith
1 | obtain local zoning rules | 2 |  | 2 | bar: 2020-04-03
2 | development permits, variances… | 2 |  | 2 | bar: 2020-04-03
3 | rough hand drawn floor plan | 1 |  | 1 | bar: 2020-04-04
4 | send sketch to Construction-Drawing.com | 1 |  | 1 | bar: 2020-04-04
5 | review quote & order code review | 1 |  | 1 | bar: 2020-04-06
6 | review proposed code review | 1 |  | 1 | bar: 2020-04-11
7 | order floor plan | 1 |  | 1 | bar: 2020-04-12
8 | review proposed floor plan | 1 |  | 1 | bar: 2020-04-17
repeat or run simultaneously:
1 | rough hand drawn exterior elevation | 1 |  | 1 | bar: 2020-04-03 to 2020-04-04; 2020-04-06; 2020-04-11 to 2020-04-12; 2020-04-17
|  | total | 11 |  | 44
Work by Construction-Drawing.com
1 | prepare quote for code review | 4 |  | 4 | bar: 2020-04-05
2 | prepare quote for drawings | 4 |  | 4 | bar: 2020-04-05
3 | prepare proposed code review | 8 |  | 8 | bar: 2020-04-07 to 2020-04-10
4 | prepare proposed floor plan | 8 |  | 8 | bar: 2020-04-13 to 2020-04-16
repeat or run consecutively:
1 | Exterior elevation (with renderings) | 8 |  | 8 | bar: 2020-04-05; 2020-04-07 to 2020-04-10; 2020-04-13 to 2020-04-16
2 | Foundation & Framing drawings | 8 |  | 8 | bar: 2020-04-05; 2020-04-07 to 2020-04-10; 2020-04-13 to 2020-04-16
|  | total | 40 |  | 64 | bar: 2020-04-05; 2020-04-07 to 2020-04-10; 2020-04-13 to 2020-04-16
Work by Builder(s)
1 | foundations | 40 |  | 40 | bar: 2020-04-18 to 2020-04-23
2 | flooring installation | 40 |  | 40 | bar: 2020-04-18 to 2020-04-23
|  | total | 80 |  | 96
insert above
fixed
can move (buffer)
preferred
can delay
tips for midifying chart
column H: use unmerge cells, drag right, re-merge cells as required
keep checking Construction-Drawing.com for updates